## Gantt Chart
Project Plan with Gantt Chart | [11 empty] | 0
Project Name: XYZ
Customer: ABC company | [7 empty] | Today's Date: | 2020-08-15 |  |  | Saturday
(vertical red line)
| Project Lead: | Zakir Hossain
| Start Date: | 2019-01-20 |  |  |  | Sunday
| End Date: | 2019-12-05 |  |  |  | Thursday
[42] | [10 empty] | First Day of Week (Sun=1): | 1 | 2019-01-20 | 2019-01-21 | 2019-01-22 | 2019-01-23 | 2019-01-24 | 2019-01-25 | 2019-01-26 | 2019-01-27 | 2019-01-28 | 2019-01-29 | 2019-01-30 | 2019-01-31 | 2019-02-01 | 2019-02-02 | 2019-02-03 | 2019-02-04 | 2019-02-05 | 2019-02-06 | 2019-02-07 | 2019-02-08 | 2019-02-09 | 2019-02-10 | 2019-02-11 | 2019-02-12 | 2019-02-13 | 2019-02-14 | 2019-02-15 | 2019-02-16 | 2019-02-17 | 2019-02-18 | 2019-02-19 | 2019-02-20 | 2019-02-21 | 2019-02-22 | 2019-02-23 | 2019-02-24 | 2019-02-25 | 2019-02-26 | 2019-02-27 | 2019-02-28 | 2019-03-01 | 2019-03-02 | 2019-03-03 | 2019-03-04 | 2019-03-05 | 2019-03-06 | 2019-03-07 | 2019-03-08 | 2019-03-09 | 2019-03-10 | 2019-03-11 | 2019-03-12 | 2019-03-13 | 2019-03-14 | 2019-03-15 | 2019-03-16 | 2019-03-17 | 2019-03-18 | 2019-03-19 | 2019-03-20 | 2019-03-21 | 2019-03-22 | 2019-03-23 | 2019-03-24 | 2019-03-25 | 2019-03-26 | 2019-03-27 | 2019-03-28 | 2019-03-29 | 2019-03-30 | 2019-03-31 | 2019-04-01 | 2019-04-02 | 2019-04-03 | 2019-04-04 | 2019-04-05 | 2019-04-06 | 2019-04-07 | 2019-04-08 | 2019-04-09 | 2019-04-10 | 2019-04-11 | 2019-04-12 | 2019-04-13 | 2019-04-14 | 2019-04-15 | 2019-04-16 | 2019-04-17 | 2019-04-18 | 2019-04-19 | 2019-04-20 | 2019-04-21 | 2019-04-22 | 2019-04-23 | 2019-04-24 | 2019-04-25 | 2019-04-26 | 2019-04-27 | 2019-04-28 | 2019-04-29 | 2019-04-30 | 2019-05-01 | 2019-05-02 | 2019-05-03 | 2019-05-04 | 2019-05-05 | 2019-05-06 | 2019-05-07 | 2019-05-08 | 2019-05-09 | 2019-05-10 | 2019-05-11 | 2019-05-12 | 2019-05-13 | 2019-05-14 | 2019-05-15 | 2019-05-16 | 2019-05-17 | 2019-05-18 | 2019-05-19 | 2019-05-20 | 2019-05-21 | 2019-05-22 | 2019-05-23 | 2019-05-24 | 2019-05-25 | 2019-05-26 | 2019-05-27 | 2019-05-28 | 2019-05-29 | 2019-05-30 | 2019-05-31 | 2019-06-01 | 2019-06-02 | 2019-06-03 | 2019-06-04 | 2019-06-05 | 2019-06-06 | 2019-06-07 | 2019-06-08 | 2019-06-09 | 2019-06-10 | 2019-06-11 | 2019-06-12 | 2019-06-13 | 2019-06-14 | 2019-06-15 | 2019-06-16 | 2019-06-17 | 2019-06-18 | 2019-06-19 | 2019-06-20 | 2019-06-21 | 2019-06-22 | 2019-06-23 | 2019-06-24 | 2019-06-25 | 2019-06-26 | 2019-06-27 | 2019-06-28 | 2019-06-29 | 2019-06-30 | 2019-07-01 | 2019-07-02 | 2019-07-03 | 2019-07-04 | 2019-07-05 | 2019-07-06 | 2019-07-07 | 2019-07-08 | 2019-07-09 | 2019-07-10 | 2019-07-11 | 2019-07-12 | 2019-07-13 | 2019-07-14 | 2019-07-15 | 2019-07-16 | 2019-07-17 | 2019-07-18 | 2019-07-19 | 2019-07-20 | 2019-07-21 | 2019-07-22 | 2019-07-23 | 2019-07-24 | 2019-07-25 | 2019-07-26 | 2019-07-27 | 2019-07-28 | 2019-07-29 | 2019-07-30 | 2019-07-31 | 2019-08-01 | 2019-08-02 | 2019-08-03 | 2019-08-04 | 2019-08-05 | 2019-08-06 | 2019-08-07 | 2019-08-08 | 2019-08-09 | 2019-08-10 | 2019-08-11 | 2019-08-12 | 2019-08-13 | 2019-08-14 | 2019-08-15 | 2019-08-16 | 2019-08-17 | 2019-08-18 | 2019-08-19 | 2019-08-20 | 2019-08-21 | 2019-08-22 | 2019-08-23 | 2019-08-24 | 2019-08-25 | 2019-08-26 | 2019-08-27 | 2019-08-28 | 2019-08-29 | 2019-08-30 | 2019-08-31 | 2019-09-01 | 2019-09-02 | 2019-09-03 | 2019-09-04 | 2019-09-05 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 2019-09-09 | 2019-09-10 | 2019-09-11 | 2019-09-12 | 2019-09-13 | 2019-09-14 | 2019-09-15 | 2019-09-16 | 2019-09-17 | 2019-09-18 | 2019-09-19 | 2019-09-20 | 2019-09-21 | 2019-09-22 | 2019-09-23 | 2019-09-24 | 2019-09-25 | 2019-09-26 | 2019-09-27 | 2019-09-28 | 2019-09-29 | 2019-09-30 | 2019-10-01 | 2019-10-02 | 2019-10-03 | 2019-10-04 | 2019-10-05 | 2019-10-06 | 2019-10-07 | 2019-10-08 | 2019-10-09 | 2019-10-10 | 2019-10-11 | 2019-10-12 | 2019-10-13 | 2019-10-14 | 2019-10-15 | 2019-10-16 | 2019-10-17 | 2019-10-18 | 2019-10-19 | 2019-10-20 | 2019-10-21 | 2019-10-22 | 2019-10-23 | 2019-10-24 | 2019-10-25 | 2019-10-26 | 2019-10-27 | 2019-10-28 | 2019-10-29 | 2019-10-30 | 2019-10-31 | 2019-11-01 | 2019-11-02 | 2019-11-03 | 2019-11-04 | 2019-11-05 | 2019-11-06 | 2019-11-07 | 2019-11-08 | 2019-11-09 | 2019-11-10 | 2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14 | 2019-11-15 | 2019-11-16 | 2019-11-17 | 2019-11-18 | 2019-11-19 | 2019-11-20 | 2019-11-21 | 2019-11-22 | 2019-11-23 | 2019-11-24 | 2019-11-25 | 2019-11-26 | 2019-11-27 | 2019-11-28 | 2019-11-29 | 2019-11-30 | 2019-12-01 | 2019-12-02 | 2019-12-03 | 2019-12-04 | 2019-12-05 | 2019-12-06 | 2019-12-07 | 2019-12-08 | 2019-12-09 | 2019-12-10 | 2019-12-11 | 2019-12-12 | 2019-12-13 | 2019-12-14 | 2019-12-15 | 2019-12-16 | 2019-12-17 | 2019-12-18 | 2019-12-19 | 2019-12-20 | 2019-12-21 | 2019-12-22 | 2019-12-23 | 2019-12-24 | 2019-12-25 | 2019-12-26 | 2019-12-27 | 2019-12-28 | 2019-12-29 | 2019-12-30 | 2019-12-31 | 2020-01-01
WBS | Tasks | Task Lead | Status | Reason/ Remarks | Start | End | Duration (Days) | % Complete | Working Days | Days Complete from Duration | Days Remaining from duration | 1: 1; 2019-01-20: 2019-01-20; 2019-01-27: 2019-01-27; 2019-02-03: 2019-02-03; 2019-02-10: 2019-02-10; 2019-02-17: 2019-02-17; 2019-02-24: 2019-02-24; 2019-03-03: 2019-03-03; 2019-03-10: 2019-03-10; 2019-03-17: 2019-03-17; 2019-03-24: 2019-03-24; 2019-03-31: 2019-03-31; 2019-04-07: 2019-04-07; 2019-04-14: 2019-04-14; 2019-04-21: 2019-04-21; 2019-04-28: 2019-04-28; 2019-05-05: 2019-05-05; 2019-05-12: 2019-05-12; 2019-05-19: 2019-05-19; 2019-05-26: 2019-05-26; 2019-06-02: 2019-06-02; 2019-06-09: 2019-06-09; 2019-06-16: 2019-06-16; 2019-06-23: 2019-06-23; 2019-06-30: 2019-06-30; 2019-07-07: 2019-07-07; 2019-07-14: 2019-07-14; 2019-07-21: 2019-07-21; 2019-07-28: 2019-07-28; 2019-08-04: 2019-08-04; 2019-08-11: 2019-08-11; 2019-08-18: 2019-08-18; 2019-08-25: 2019-08-25; 2019-09-01: 2019-09-01; 2019-09-08: 2019-09-08; 2019-09-15: 2019-09-15; 2019-09-22: 2019-09-22; 2019-09-29: 2019-09-29; 2019-10-06: 2019-10-06; 2019-10-13: 2019-10-13; 2019-10-20: 2019-10-20; 2019-10-27: 2019-10-27; 2019-11-03: 2019-11-03; 2019-11-10: 2019-11-10; 2019-11-21: 2019-11-21; 2019-11-28: 2019-11-28; 2019-12-05: 2019-12-05; 2019-12-12: 2019-12-12; 2019-12-19: 2019-12-19; 2019-12-26: 2019-12-26
0 | Project Start and End |  |  |  | 2019-01-12 | 2019-12-05 | 328 | #REF! | 234 | #REF! | #REF!
1 | SRS / BRD Collection |  |  |  | 2019-01-22 | 2019-04-17 | 86 | 100% | 62 | 86
1.1 | Meetings, Requirement Collection, Review, BRD Preparation, WorkFlow Document SRS Design, Presentations, Documentation |  | Done |  | 2019-01-22 | 2019-03-20 | 58 | 100% | 42 | 58
1.2 | SRS Subbmission for Approval |  | Done |  | 2019-03-28 | 2019-03-28 | 1 | 100% | 1 | 1
1.3 | SRS Review Session |  | Done |  | 2019-04-07 | 2019-04-17 | 11 | 100% | 8 | 11
2 | Development |  |  |  | 2019-01-12 | 2019-07-08 | 178 | 100% | 126 | 178 | 0
2.1 | Process Engine Development |  | Done |  | 2019-01-12 | 2019-02-25 | 45 | 100%
2.2 | Business Logic Engine Development |  | Done |  | 2019-02-26 | 2019-03-27 | 30 | 100%
2.3 | Form Engine Development |  | Done |  | 2019-03-28 | 2019-04-24 | 28 | 100%
2.4 | Authintication Process |  | Done |  | 2019-04-25 | 2019-05-24 | 30 | 100%
2.5 | User, Role, Group and Master Data Management |  | Done |  | 2019-05-25 | 2019-06-13 | 20 | 100%
2.6 | Document Management |  | Done |  | 2019-06-14 | 2019-07-08 | 25 | 100%
3 | Process 1 |  |  |  | 2019-10-17 | 2019-11-25 | 40 | 82.7% | 28 | 33 | 7
3.1 | Requirement Finalization Understanding |  | Done |  | 2019-10-17 | 2019-10-26 | 10 | 100%
3.2 | Delivery API |  | Pending |  | 2019-10-17 | 2019-10-18 | 2 | 0%
3.3 | Development |  | In Progress |  | 2019-10-19 | 2019-11-20 | 33 | 95% | 1 | 31 | 2
3.4 | UI and Flow Demonstration w/o integration |  | Scheduled |  | 2019-11-21 | 2019-11-21 | 1 | 0%
3.5 | Fix Observation |  | Scheduled |  | 2019-11-22 | 2019-11-24 | 3 | 0%
3.6 | UAT w/o Integration |  | Scheduled |  | 2019-11-25 | 2019-11-25 | 1 | 0%
3.7 | Integration with API |  | TBD | Depending on API readyness |  |  |  | 0%
3.8 | UAT with API |  | TBD |  |  |  |  | 0%
4 | Process 2 |  |  |  | 2019-10-17 | 2019-12-05 | 50 | 59.57% | 36 | 29 | 21
4.1 | Requirement Finalization Understanding |  | In Progress |  | 2019-10-17 | 2019-10-26 | 10 | 100%
4.2 | Delivery API |  | Pending |  | 2019-10-17 | 2019-10-18 | 2 | 0%
4.3 | Development |  | In Progress |  | 2019-11-02 | 2019-11-30 | 29 | 60% | 20 | 17 | 12
4.4 | UI and Flow Demonstration w/o integration |  | Scheduled |  | 2019-12-01 | 2019-12-01 | 1 | 0%
4.5 | Fix Observation |  | Scheduled |  | 2019-12-02 | 2019-12-04 | 3 | 0%
4.6 | UAT w/o Integration |  | Scheduled |  | 2019-12-05 | 2019-12-05 | 1 | 0%
4.7 | Integration with API |  | TBD | Depending on API readyness |  |  |  | 0%
4.8 | UAT with API |  | TBD |  |  |  |  | 0%
Note on A10: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … The WBS is automatically entered, but the formulas are different for different levels.
Note on F10: Start Date Enter the starting date for this task. To associate the start date with the end of another task, enter a formula in the start date that refers to the end date of that task.
Note on G10: End Date The ending date is calculated by adding the Duration (calendar days) to the Start date minus 1 day, because the task duration is from the beginning of the Start day to the end of the End day.
Note on H10: Duration (Calendar Days) Enter the number of calendar days for the given task. Refer to the Working Days column or use a calendar to determine the corresponding working days. The duration is from the beginning of the Start date to the ending of the End Date. When the duration is calculated, it is calculated as End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day.
Note on I10: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on J10: Working Days Counts the number of working days using the NETWORKDAYS() formula, which excludes weekends. When planning work based upon the number of working days, adjust the Duration until the desired # of working days is reached.
Note on K10: Calendar Days Complete This column is calculated by multiplying the Duration by the %Complete and rounding down to the nearest integer.
Note on L10: Calendar Days Remaining This column is calculated by subtracting the Days Complete from the Duration.